**Time Schedule for Completion of** [**IEEE GLSVLSI 2023 Conference Paper**](https://www.glsvlsi.org/)

|  |  |
| --- | --- |
| **Step** | **Deadline** |
| Understand Assignments and Tasks | Done |
| Have a General Research Topic | Done |
| Discover, Narrow, and Focus on a Topic | Done |
| Determine Research Objectives and New Ideas | December 04, 2022 (11:59 PM - EST) |
| Find, Select, and Read Important Resources | December 06, 2022 (11:59 PM - EST) |
| Group, Sequence, and Document Information | December 08, 2022 (11:59 PM - EST) |
| Prepare Preliminary Research Materials | December 11, 2022 (11:59 PM - EST) |
| Write a Research Outline | December 16, 2022 (11:59 PM - EST) |
| Build All Required Materials | January 16, 2023 (11:59 PM - EST) |
| Write Paper Abstract | January 17, 2023 (11:59 PM - EST) |
| Write Paper Conclusion | January 17, 2023 (11:59 PM - EST) |
| Write Paper Body | January 24, 2023 (11:59 PM - EST) |
| Send Final Draft to Research Advisor (Dr. Taheri) | January 27, 2023 (11:59 PM - EST) |
| Submit Paper to Conference | February 6, 2023 (11:59 PM - EST) |